Intelligent Credit Card & Rewards Optimization Agent

Engineering Implementation Guide

Document class: Senior Engineering Design Document

Audience: Development team, tech lead, engineering manager, future maintainers

Companion document: Intelligent Credit Card & Rewards Agent — Solution Architecture & Product Documentation

Version 1.0  |  Status: Draft for Review

Table of Contents

1. Project Understanding

2. Development Strategy

3. Overall Development Workflow

4. Environment Setup

5. Folder Structure

6. Database Implementation Workflow

7. Data Collection Workflow

8. PDF Processing Workflow

9. Embedding Pipeline

10. Vector Database Workflow

11. Structured Data Extraction

12. Backend Development Workflow

13. AI Agent Development Workflow

14. LangGraph Workflow

15. Prompt Engineering Workflow

16. API Development Workflow

17. Frontend Development Workflow

18. Testing Workflow

19. Monitoring Workflow

20. Deployment Workflow

21. Development Timeline

22. Coding Standards

23. Suggestions & Best Practices

24. Common Pitfalls

25. Final Technical Recommendations

# 1. Project Understanding

## 1.1 The Problem, Restated as an Engineering Brief

We are building a system that takes a natural-language spending scenario, retrieves the governing reward rules for the user's owned cards from a corpus of issuer documents, performs a deterministic calculation, and returns a cited, explainable recommendation — refusing to guess when evidence is weak, and requiring explicit human confirmation before any irreversible action (point transfer) is finalized.

As a Tech Lead, I want the team to internalize one governing constraint before writing a single line of code: this is a system where the cost of a confident wrong answer is real money for the user. Every subsequent architectural decision in this document — the RAG layer, the separation of the calculator from the LLM, the guardrail node, the human-approval gate — is a direct consequence of that constraint, not an independent feature to be built in isolation.

## 1.2 Why the Proposed Architecture Is Suitable

The companion architecture document specifies RAG + LangGraph agent + tool-calling + guardrails + human-in-the-loop. From an engineering-feasibility standpoint, this is the right shape because it maps cleanly onto three orthogonal concerns that must never leak into each other:

| Concern | Owned by | Why it must stay separate |
| --- | --- | --- |
| Facts (what does the card's T&C actually say) | Retrieval layer (RAG) | Facts change over time and must be sourced, versioned, and citable — not memorized by the LLM |
| Arithmetic (what is the reward worth) | Calculator tool (deterministic code) | LLMs are unreliable at multi-step arithmetic; a bug in a hand-written function is debuggable, a bug in an LLM's mental math is not |
| Judgment (what should the user do, and how do we explain it) | LLM + guardrail node | This is the only part of the system where natural-language generation is actually the right tool |

A team that blurs these boundaries — e.g., asking the LLM to "retrieve and calculate in one prompt" — will ship a system that is fast to demo and impossible to debug or trust in week 3. This document is written to prevent that outcome.

## 1.3 Overall Engineering Approach

We will build in thin vertical slices that each produce a demoable, evaluable increment, not in horizontal layers that only come together at the end (see Section 2 for the full argument). Every phase in Section 3 ends with something a non-engineer could watch work.

## 1.4 Expected Challenges

| Challenge | Why it will happen | When it will bite |
| --- | --- | --- |
| Retrieval returning the right card's rule vs. a plausible-sounding wrong-card rule | Embedding similarity doesn't respect card boundaries by default | As soon as you load more than 2 cards |
| Arithmetic drift if the LLM is ever allowed to "help" with a calculation | Autoregressive generation is not arithmetic | The first time someone removes the calculator tool "to simplify the prompt" |
| Chunking that splits a reward rate from its cap/exclusion clause | Naive fixed-length chunking ignores document structure | Silent — will not show up until an evaluation run specifically checks for it |
| Guardrail node becoming a rubber stamp | Teams under deadline pressure weaken guardrails instead of fixing root causes | Right before a demo, under time pressure — the exact wrong time |
| Scope creep from the "Suggestions" list (Section 23) | Every item is individually a good idea | Any time before the MVP is stable |

# 2. Development Strategy

## 2.1 Options Considered

| Strategy | Description | Fit for this project |
| --- | --- | --- |
| Feature-first | Build one user-facing feature completely (UI to DB) before starting the next | Good instinct, but too coarse-grained for an agentic system — "recommendation" is not one feature, it's a pipeline |
| Layer-first | Build all of the DB layer, then all of the API layer, then all of the agent layer, then the UI | Common but risky here: you cannot validate retrieval quality or agent behavior until every layer exists, meaning the first real signal on the hardest problem (RAG correctness) arrives last |
| Domain-driven design (DDD) | Organize around bounded contexts (Cards, Rewards, Recommendations, Users) with rich domain models | Conceptually appealing, but heavyweight for a project of this scope — the domain is not complex enough to justify aggregate roots, domain events, and repositories-per-aggregate at MVP stage |
| Vertical slice architecture | Build one complete, thin, end-to-end path (e.g., "single-transaction recommendation") through every layer, then add the next slice | Recommended |

## 2.2 Recommendation: Vertical Slice Architecture, DDD-Informed Naming

Build in vertical slices — each slice is a complete path from API request to final answer for one use case (Stage 1: single-transaction recommendation; Stage 2: monthly optimization; Stage 3: transfer strategy with approval) — while borrowing DDD's naming and boundary discipline (Cards, Rewards, Recommendations as named concepts in code) without adopting its full tactical pattern set (no aggregate roots, no domain events bus, at this scale).

Why this wins for this specific project:

- Fastest path to your highest-risk unknown. The riskiest unknown in this project is not "can we build a REST API" — it's "can retrieval + calculation reliably produce a correct, grounded answer." A vertical slice gets you a testable answer to that question in week 2, not week 8.

- Matches the staged roadmap already defined in the architecture document. Stage 1 (MVP RAG), Stage 2 (orchestration/memory), Stage 3 (guardrails/approval) are already vertical slices in disguise — this strategy just names that explicitly and carries it into code organization.

- Every slice is independently demoable and evaluable. This matters enormously for a capstone project, where "show me it working" moments are graded events, not just internal milestones.

- Avoids DDD overhead the team doesn't need yet. A solo/small team maintaining aggregate roots and domain events for a system with six database tables is solving a problem it doesn't have.

Trade-off to accept knowingly: vertical slices can produce some duplicated logic across slices early on (e.g., card-lookup logic touched by both the single-transaction and monthly-optimization slices). The mitigation is not to prematurely abstract — extract shared logic into services/ only when the third slice needs it (the standard "rule of three"), not the second.

# 3. Overall Development Workflow

Each phase below is a vertical slice per Section 2. Durations assume 1–2 developers at a capstone/early-stage pace (10–15 focused hours/week per person).

## Phase 0 — Foundation

- Objective: Repository, environment, CI skeleton, and empty-but-running service exist.

- Deliverables: Git repo with branching model live; docker-compose up brings up an empty FastAPI app + Postgres; pre-commit hooks pass on an empty commit.

- Dependencies: None.

- Acceptance criteria: GET /health returns 200 from a container; CI pipeline runs (even if it only lints).

- Risks: Over-engineering the skeleton before there's a feature to justify it.

- Estimated duration: 2–3 days.

- Expected output: A boring, working "hello world" that the whole rest of the project builds on.

## Phase 1 — Vertical Slice: Single-Transaction Recommendation (MVP)

- Objective: End-to-end path: ingest 4–5 card PDFs → chunk → embed → store → retrieve → calculate → return a cited answer, via CLI or a single API endpoint (UI optional at this stage).

- Deliverables: Ingestion script; document_chunks table populated; retriever function; calculator tool with unit tests; /recommend endpoint (non-streaming is fine); 20 golden test questions (per the architecture doc).

- Dependencies: Phase 0.

- Acceptance criteria: All 20 golden questions produce a plausible, cited answer; calculator has 100% unit test pass rate on hand-computed expected values; retrieval precision@5 ≥ 0.75 on the golden set.

- Risks: Underestimating chunking quality issues (see Section 8) — budget explicit time to inspect chunks manually, not just trust the pipeline ran without error.

- Estimated duration: 3–4 weeks.

- Expected output: A CLI or minimal API that correctly answers "I'm spending ₹50,000 on flights, which card?" with citations.

## Phase 2 — Vertical Slice: Orchestration, Memory, Monthly Optimization

- Objective: Replace the single-shot pipeline with a LangGraph agent; add conversation memory; add the monthly-spend-optimization use case (which requires classifying spend into categories and comparing across cards).

- Deliverables: LangGraph graph with Intent Classification, Retrieval, Rule Validation, Calculation, Comparison nodes; user_profiles table; spend-category classifier; expanded golden set (40+ questions covering both use cases).

- Dependencies: Phase 1's retriever and calculator, reused as LangGraph tools.

- Acceptance criteria: Multi-turn conversations correctly retain stated preferences within a session; monthly-optimization queries correctly allocate spend across ≥3 cards with cited rules per category.

- Risks: Scope creep — resist adding transfer-strategy logic here; that's Phase 3.

- Estimated duration: 3–4 weeks.

- Expected output: A conversational agent that handles both single-transaction and monthly-optimization queries with memory.

## Phase 3 — Vertical Slice: Guardrails, Human Approval, Transfer Strategy, UI

- Objective: Add the Guardrail Node, the Human Approval interrupt/resume flow, the transfer-strategy use case, and a Streamlit UI wrapping the API.

- Deliverables: Guardrail Node with unit tests independent of LLM output; Human Approval node using LangGraph interrupt/resume; /transfer/evaluate and /transfer/confirm endpoints; Streamlit UI with confirm/cancel buttons; monitoring via LangSmith or Phoenix.

- Dependencies: Phase 2's full agent graph.

- Acceptance criteria: No transfer calculation is ever finalized without an explicit approval step observed in a trace; guardrail node blocks at least one deliberately-injected "invented rule" test case in a red-team test; full demo flow (ingest → query → clarify → approve → recommend) runs live without manual intervention.

- Risks: Guardrail rules becoming either too strict (excessive refusals) or too lax (rubber-stamping) — calibrate against the golden set, not by feel.

- Estimated duration: 3–4 weeks.

- Expected output: The full demoable system described in the architecture document's Section 18 (Capstone Demo Flow).

## Phase 4 — Evaluation, Hardening, Documentation, Buffer

- Objective: Run the full evaluation harness (Section 18 of this doc), fix regressions, write the final report, record the demo.

- Deliverables: Evaluation report; README; architecture diagrams; demo video.

- Dependencies: Phase 3.

- Acceptance criteria: Hallucination rate on golden set = 0%; calculation accuracy = 100%; README allows a stranger to run the project from a clean clone in under 30 minutes.

- Risks: Treating this phase as optional under time pressure — it is not; an ungraded, unevaluated system is a demo, not an engineering deliverable.

- Estimated duration: 1–2 weeks.

- Expected output: A submittable, portfolio-ready capstone.

# 4. Environment Setup

| Decision | Recommendation | Why |
| --- | --- | --- |
| Python version | 3.11 or 3.12 | Mature async support, broad compatibility with LangChain/LangGraph as of 2026, meaningfully faster than 3.9/3.10 |
| Virtual environment | venv + pip-tools, or uv if the team is comfortable with it | venv is zero-dependency and universally understood; uv is materially faster for a small team willing to adopt a newer tool — recommend uv if starting fresh in 2026, venv if optimizing for reviewer/grader familiarity |
| Dependency management | requirements.in → compiled to pinned requirements.txt via pip-compile (or uv pip compile) | Pinned, reproducible builds; separates "what I want" from "what got resolved" |
| IDE | VS Code with Python, Pylance, Ruff, and Docker extensions | Best-in-class free tooling; consistent across team members regardless of OS |
| Docker setup | docker-compose.yml with app, db (Postgres+pgvector), and optionally ui services | Matches the deployment architecture in the companion document; makes onboarding a one-command operation |
| Git strategy | Trunk-based development with short-lived feature branches | At small team scale, long-lived branches (GitFlow) create more merge pain than they prevent; trunk-based with feature flags (Section 23) for anything risky |
| Branching model | main (always deployable) + feature/<slice-name> branches merged via PR | Matches the vertical-slice strategy: one branch per slice, not per layer |
| Environment variables | .env (gitignored) + .env.example (committed) | Standard 12-factor practice; .env.example documents required config without leaking secrets |
| Secrets management | Local: .env via python-dotenv. Deployed: platform secret manager (e.g., cloud provider's secret store) injected as environment variables | Never commit secrets; never pass secrets as CLI arguments (they leak into shell history and process lists) |
| Pre-commit hooks | pre-commit framework running Ruff (lint+format) and mypy (type check) on every commit | Catches issues before they reach CI, which is faster feedback for the developer |
| Linting/Formatting | Ruff for both linting and formatting | As of 2025–2026, Ruff has effectively superseded the separate flake8+black+isort combination for Python projects — one fast tool instead of three |
| Type checking | mypy in --strict mode on agents/, tools/, and database/models.py at minimum | Type-checking the boundaries (tool inputs/outputs, DB models) catches the highest-value class of bugs for the least annotation effort; full-strict everywhere is a nice-to-have, not a blocker |
| Testing setup | pytest + pytest-asyncio (for FastAPI async routes) + pytest-cov | Industry standard; async support is required given FastAPI's async-first design |

# 5. Folder Structure

credit-card-rewards-agent/ ├── app/ │ └── streamlit_app.py # MVP UI — thin, calls the API only ├── backend/ │ ├── main.py # FastAPI app factory, router registration │ ├── config.py # Pydantic Settings — all env vars typed here │ └── api/ │ ├── routes_recommend.py │ ├── routes_transfer.py │ ├── routes_user.py │ └── routes_admin.py ├── agents/ │ ├── graph.py # LangGraph graph assembly │ ├── nodes/ │ │ ├── intent.py │ │ ├── clarify.py │ │ ├── retrieve.py │ │ ├── validate.py │ │ ├── calculate.py │ │ ├── compare.py │ │ ├── guardrail.py │ │ ├── approval.py │ │ └── final_answer.py │ ├── state.py # TypedDict/Pydantic agent state schema │ └── prompts/ │ ├── system_prompt.py │ ├── intent_prompt.py │ └── ... # one file per prompt, versioned (Section 15) ├── tools/ │ ├── calculator.py # pure, deterministic, framework-agnostic │ ├── retriever.py # wraps vector search + metadata filtering │ └── transfer_calculator.py ├── rag/ │ ├── ingest_pdfs.py │ ├── chunk_documents.py │ ├── embed_documents.py │ └── retrieval.py ├── database/ │ ├── models.py # SQLAlchemy models │ ├── db.py # engine/session management │ ├── migrations/ # Alembic migrations │ └── seed.py ├── data/ │ ├── raw_pdfs/ │ ├── processed_chunks/ │ ├── sample_queries.csv │ └── golden_answers.csv ├── evaluation/ │ ├── rag_eval.py │ ├── calculation_eval.py │ └── hallucination_eval.py ├── monitoring/ │ ├── langsmith_config.py │ └── custom_logger.py ├── tests/ │ ├── unit/ │ ├── integration/ │ └── agent/ ├── docs/ │ └── architecture-diagrams/ ├── .env.example ├── docker-compose.yml ├── Dockerfile ├── requirements.in / requirements.txt ├── pyproject.toml # Ruff + mypy + pytest config └── README.md

## 5.1 Naming Conventions

- Files/modules: snake_case.py.

- Classes: PascalCase (RewardRule, CalculatorInput).

- Functions/variables: snake_case.

- Agent node functions: verb-first (classify_intent, validate_rules) so the graph definition in graph.py reads like a sentence.

- Environment variables: UPPER_SNAKE_CASE, prefixed by concern (DB_, LLM_, LANGSMITH_).

## 5.2 Why This Structure Scales

The critical separation is tools/ vs agents/: tools are plain, framework-agnostic Python functions with no LangGraph/LangChain imports. This means the calculator and retriever can be unit-tested in isolation, reused outside the agent (e.g., in a batch evaluation script or a future non-chat interface), and swapped to a different orchestration framework later without rewriting business logic — only agents/graph.py would need to change.

# 6. Database Implementation Workflow

## 6.1 Design-First, Then Migrate

Start from the ER diagram in the architecture document (six tables: card_documents, document_chunks, reward_rules, transfer_partners, user_profiles, recommendation_logs). Write the SQLAlchemy models first, then generate the initial Alembic migration from them — never hand-write the first migration, since models and schema will drift if authored independently.

## 6.2 Migration Strategy

- Use Alembic for all schema changes, from day one — even in Phase 0, before there's real data to lose. Retrofitting migrations onto a hand-evolved schema later is one of the most common and avoidable sources of lost time in small projects.

- One migration per logical schema change, not one giant migration per phase. This keeps alembic downgrade actually usable during development.

- Never edit an already-applied migration file; write a new one to fix it (the same discipline as never force-pushing shared git history).

## 6.3 Indexes

- document_chunks.embedding: hnsw index (pgvector) — generally preferred over ivfflat for pgvector as of recent versions due to better recall at comparable speed, at the cost of slightly slower build time, which is irrelevant at this project's data scale.

- reward_rules(card_name, spend_category): composite B-tree index — this is the calculator's primary lookup path and will be hit on every single query.

- recommendation_logs(user_id, created_at): supports the reporting/history endpoints without a full table scan.

## 6.4 Relationships

Foreign keys from document_chunks, reward_rules, and transfer_partners back to card_documents.document_id enable the critical audit trail: every numeric claim in a final answer must be traceable back to a specific document and its effective_date. Enforce these as actual DB foreign key constraints, not just application-level convention — this catches ingestion bugs (orphaned chunks) immediately rather than silently.

## 6.5 Versioning Card Data

Do not overwrite a card's rules when terms change. Insert a new card_documents row with a new effective_date and re-run ingestion for that card, leaving old rows queryable. This is what makes "as of what date was this recommendation accurate" answerable later — a non-negotiable requirement given the compliance considerations in the architecture document's Section 18.

## 6.6 Seed / Mock / Test Data

- Seed data: the 4–5 real, manually-curated cards for local development — checked into data/raw_pdfs/ (or a small subset, respecting any redistribution concerns) with a seed.py script that ingests them into a fresh DB.

- Mock data: a small set of synthetic, clearly-fake card rules (e.g., "Test Card Alpha") for unit tests, so tests never depend on real card data changing.

- Test data: the golden dataset (Section 18) — kept separate from both seed and mock data, version-controlled, and treated as a first-class project artifact, not a scratch file.

## 6.7 Backup Strategy

Nightly pg_dump to local/cloud storage is sufficient at capstone scale. Document the restore procedure in the README even if it's never needed — an untested backup is not a backup.

# 7. Data Collection Workflow

## 7.1 Sourcing

Use only official, publicly published issuer documents (T&Cs, reward program PDFs, MITC — Most Important Terms and Conditions — documents) obtained directly from issuer websites. Do not scrape aggregator/forum content as a primary source — it is unofficial, may be stale, and scraping at scale raises the ToS concerns flagged in the architecture document's risk analysis. Community sources (Technofino, etc.) are acceptable as a secondary cross-check, never as the system's ground truth.

## 7.2 Validation Before Ingestion

Before a document enters the pipeline, manually confirm: it is the current version (check any "last updated" date on the issuer's page), it is a T&C/MITC document and not marketing collateral, and it has a text layer (not a pure scan) or is flagged for OCR (Section 8.6).

## 7.3 Cleaning and Organization

- Store raw PDFs untouched in data/raw_pdfs/<issuer>/<card_name>/<effective_date>.pdf — this path structure alone encodes most of the metadata needed later.

- Never edit a raw PDF in place; all cleaning happens downstream in the extraction pipeline (Section 8), preserving the source artifact for audit purposes.

## 7.4 Version Control for Documents

Raw PDFs are binary and don't diff well in Git — track them with Git LFS if committed to the repo at all, or better, keep them in a separate object store (e.g., cloud storage bucket) referenced by URL in card_documents.source_url, keeping the code repository lightweight.

## 7.5 Update Strategy

Set a recurring (e.g., quarterly) manual review cadence per card to check for T&C changes, since no reliable push-notification exists for most issuers. This is explicitly a manual, human process at MVP/Phase 2 scale — automating "detect when an issuer changed their terms" is a Future Scope item (see the architecture document's Section 23), not a Phase 1 requirement.

## 7.6 Document Metadata

Capture at minimum: card_name, issuer, document_type, effective_date, source_url, uploaded_at — this is the card_documents table, and it should be populated before chunking begins, not inferred after the fact from chunk content.

# 8. PDF Processing Workflow

## 8.1 Text Extraction

| Library | Strengths | Weaknesses | Recommendation |
| --- | --- | --- | --- |
| PyMuPDF (fitz) | Fast, handles complex layouts and tables reasonably well, actively maintained | Slightly more complex API | Recommended |
| pdfplumber | Excellent table extraction, simple API | Slower on large documents | Good secondary tool specifically for table-heavy pages (reward-rate tables) |
| pypdf | Pure Python, no system dependencies | Weaker layout/table handling | Avoid as primary extractor for this domain given how table-heavy card T&Cs are |

Recommended approach: PyMuPDF as the primary extractor; fall back to pdfplumber specifically for pages detected to contain tables (a heuristic: high density of numeric tokens and short lines), since reward-rate tables are exactly the content this project cares most about getting right.

## 8.2 Cleaning

Strip repeated headers/footers (page numbers, "Terms and Conditions v3.2" boilerplate) that would otherwise pollute every chunk. Detect these via repetition across pages (a line appearing near-identically on >80% of pages is almost certainly boilerplate, not content).

## 8.3 Normalization

Normalize currency symbols, whitespace, and Unicode variants (e.g., different dash characters) before chunking — inconsistent normalization is a common, invisible cause of retrieval quality problems, since two semantically identical clauses can embed differently if their surface text differs in encoding.

## 8.4 Chunking Strategy

| Approach | Description | Fit |
| --- | --- | --- |
| Fixed-length character/token chunking with overlap | Simple, standard RAG default | Baseline — acceptable for Phase 1, but risks splitting a reward rate from its cap clause |
| Recursive character splitting (LangChain's RecursiveCharacterTextSplitter) | Fixed-length but respects paragraph/sentence boundaries when possible | Better baseline than naive fixed-length; recommended for Phase 1 |
| Structure-aware chunking (split on detected headings/clauses/table boundaries) | Chunks align with the document's actual logical units | Recommended for Phase 2+ once naive chunking's failure modes are observed in evaluation |

Start with recursive character splitting (~400–600 tokens, ~50-token overlap) to get Phase 1 moving quickly. Budget explicit time in Phase 2 to inspect golden-set failures and move to structure-aware chunking for any card where a cap/exclusion clause is getting separated from its reward rate — this is a data-quality investment, not a nice-to-have, because it directly determines whether the calculator ever receives a complete rule.

## 8.5 Metadata Extraction

Attach card_name, issuer, document_type, page_number, effective_date, and source_url to every chunk at chunking time (not retrieval time) — metadata generated lazily at query time is both slower and a common source of subtle bugs (e.g., stale joins).

## 8.6 Failure Handling

- No text layer detected (scanned PDF): flag the document for OCR (Tesseract or a cloud OCR service) rather than silently producing empty chunks. Never ingest a zero-content document without an explicit error/warning surfaced to the admin.

- Extraction produces garbled text (common with poorly-encoded PDFs): run a basic sanity check (ratio of recognizable words to total tokens) and reject/flag documents below a threshold rather than embedding garbage.

## 8.7 Quality Validation

Before a newly-ingested document is considered "live," manually spot-check a sample of its chunks against the source PDF. This is a 15-minute human task per document that catches the majority of extraction bugs before they propagate into wrong recommendations — cheap insurance relative to the cost of a bad answer reaching a golden-set evaluation or, worse, a user.

# 9. Embedding Pipeline

## 9.1 Embedding Model Selection

| Option | Cost | Quality | Privacy | Recommendation |
| --- | --- | --- | --- | --- |
| OpenAI text-embedding-3-small | Low | Good | Data sent to OpenAI | Recommended for MVP — best cost/quality trade-off for a capstone budget |
| OpenAI text-embedding-3-large | Higher | Best | Data sent to OpenAI | Consider for Phase 3 if evaluation shows the small model missing nuanced distinctions (e.g., "excluded" vs. "capped") |
| Open-source (e.g., BGE, E5 family) via local inference | Free (compute only) | Competitive, sometimes requires fine-tuning to match closed models on niche domains | Fully private | Best choice if data privacy is a hard requirement or API cost must be zero — accept the added infra complexity of hosting inference |

Recommendation: start with text-embedding-3-small for velocity; treat swapping to an open-source model as a contained, well-isolated change because the retriever tool (Section 5) already isolates embedding calls behind one interface.

## 9.2 Generation, Storage, Caching

- Generate embeddings in a batch script (embed_documents.py), never inline during a live user query for ingestion-time content — only the user's query is embedded at request time.

- Cache embeddings by a hash of (chunk_text + model_version) so re-running ingestion after a code change doesn't re-embed unchanged chunks — this matters once the corpus grows past a handful of cards, both for cost and for iteration speed.

- Store the embedding model name/version alongside each vector (document_chunks.metadata_json) — mixing vectors from two different embedding models in one index silently corrupts similarity search, since distances are not comparable across models.

## 9.3 Batch Processing

Batch embedding API calls (most providers support batching many texts per request) rather than one call per chunk — this is a straightforward, high-value cost and latency optimization with no downside.

## 9.4 Re-indexing

When a card document is updated (Section 6.5), re-embed only the new document's chunks; do not delete or re-embed unrelated cards' chunks. Re-indexing should be a targeted, auditable operation tied to a specific document_id, never a "wipe and rebuild everything" script run casually.

# 10. Vector Database Workflow

## 10.1 Database Selection

Per the architecture document's Section 15: pgvector for MVP through Phase 3, given the project's scale (low thousands of chunks) and the benefit of co-locating structured and vector data in one Postgres instance. Revisit only if corpus size or concurrent query load grows materially past capstone scale.

## 10.2 Collection ("Table") Design

A single document_chunks table with a card_name metadata column, rather than one table/collection per card. This keeps cross-card comparison queries (needed for the Comparison Node) simple joins/filters instead of fan-out queries across multiple tables.

## 10.3 Metadata Filters

Every retrieval query should filter by card_name (when the user's owned cards are known) before or alongside the vector similarity search — never rely on similarity ranking alone to keep results within the correct card's rules. This directly addresses the "wrong-card rule retrieved" risk flagged in the architecture document's risk analysis.

## 10.4 Hybrid Search

Phase 1: pure vector similarity is acceptable. Phase 2+: add keyword/BM25 matching (e.g., via Postgres full-text search tsvector, combined with vector similarity in a weighted re-ranking step) to catch exact-term queries (specific merchant names, exact card product names) that embeddings alone can under-rank.

## 10.5 Ranking and Similarity Thresholds

Set an explicit minimum similarity threshold below which retrieved chunks are discarded rather than passed to the LLM — a low-confidence chunk being fed into the prompt "just in case" is precisely how ungrounded-sounding answers happen. Tune this threshold empirically against the golden set, not by intuition; too high a threshold causes false "insufficient information" refusals, too low causes hallucination risk.

## 10.6 Performance Optimization

At this project's scale, performance optimization (index tuning, connection pooling) is a Phase 3+ concern, not a Phase 1 one — do not spend Phase 1 time tuning hnsw parameters for a corpus of a few thousand chunks; that time is far better spent on chunking and retrieval correctness.

# 11. Structured Data Extraction

## 11.1 Manual vs. AI-Assisted Extraction

| Approach | Description | Trade-off |
| --- | --- | --- |
| Fully manual | A human reads each card's T&C and hand-populates reward_rules rows | Highest accuracy, but doesn't scale past a handful of cards; recommended for the 4–5 card MVP |
| AI-assisted extraction with mandatory human review | LLM proposes structured rows from retrieved chunks; a human reviews/approves before the row is marked "active" | Recommended for Phase 2+ / scaling beyond 5 cards — this is the correct middle ground: AI does the tedious first pass, a human remains the final authority |
| Fully automated, no review | LLM extraction is trusted and inserted directly | Not recommended at any phase for this domain — an unreviewed extraction error becomes a silently wrong reward rate driving real financial recommendations |

## 11.2 Validation Process

Every extracted reward_rules row carries a confidence_score and a source_chunk_id. A row below a confidence threshold (whether extracted manually with self-reported low confidence, or by an AI-assisted pass) is flagged pending_review and excluded from live retrieval until a human approves it — this is the data-side analog of the human-approval node on the user-facing side.

## 11.3 Conflict Resolution

When two chunks from the same card document appear to state different reward rates for the same category (a real occurrence, e.g., an "up to" headline rate vs. a category-capped effective rate), do not let extraction silently pick one — flag the conflict for human resolution and store both candidate rows with a conflict_flag, resolved before either becomes "active."

## 11.4 Updating

When a card's terms change (Section 6.5), extraction re-runs against the new document version only; previous reward_rules rows are not deleted, just superseded (their governing card_documents.effective_date puts them in the past for any query asking "what was true as of date X").

# 12. Backend Development Workflow

## 12.1 Recommended Implementation Order

Build backend layers in this order — each step should be independently testable before moving to the next:

- Configuration (config.py, Pydantic Settings) — nothing else can be tested without this existing first.

- Database (models, migrations) — the schema is the contract everything else depends on.

- Repositories (thin data-access functions/classes wrapping SQLAlchemy queries) — isolates SQL from business logic.

- Tools (calculator.py, retriever.py) — pure functions, unit-testable in complete isolation from the database and the LLM.

- Services (business logic that composes repositories + tools, e.g., "given a query, produce a recommendation") — this is where retrieval + calculation + comparison get orchestrated before wrapping in LangGraph, which is a deliberate sequencing choice: prove the logic works as plain function calls before adding agent-graph complexity on top.

- Agent graph (LangGraph wrapping the services as tools/nodes) — Section 13–14.

- API layer (FastAPI routes calling the agent graph) — Section 16.

- Authentication — added once there's a real multi-user concern (Stage 2+, per the architecture document's FR-1).

- Logging & error handling — woven in throughout, but hardened as an explicit pass at the end of each phase, not left until Phase 4.

Why this order: the single biggest risk-reduction move is step 5 — validating that retrieval + calculation logic is correct as plain, synchronous, debuggable Python function calls before it's wrapped in an agent graph, where a bug can hide behind non-deterministic LLM behavior and be much harder to isolate.

## 12.2 Error Handling Philosophy

Distinguish three error classes explicitly in code, not just in prose:

- Validation errors (bad input, e.g., negative spend) → HTTP 422, never reach the agent.

- Domain refusals (insufficient retrieved evidence) → a normal, successful response whose content is "I don't have enough information" — this is a feature, not an error, and must not be implemented as an exception/500.

- System failures (DB down, LLM API down) → HTTP 503 with a clear message; retried with backoff at the service layer before surfacing to the user.

# 13. AI Agent Development Workflow

## 13.1 Recommended Build Order

Build and test agent components bottom-up — tools and validators before the LLM-driven nodes that call them, so that when something goes wrong you already know the deterministic layer is correct and can focus debugging on the non-deterministic layer:

- Calculator tool — fully deterministic, no LLM involved; write exhaustive unit tests first (Section 18). This is the foundation everything else calls.

- Retriever — wraps vector search; testable against the golden set's expected-chunk annotations without any LLM in the loop.

- Rule validator — a mostly-deterministic check ("is there at least one chunk above threshold that mentions this category") with a thin LLM-assisted layer only for ambiguous cases; build the deterministic check first.

- Intent classifier — first LLM-dependent component; small, focused prompt with a constrained output schema (an enum of intents), evaluated against a labeled test set before wiring into the graph.

- Comparison engine — mostly arithmetic (calls the calculator per candidate card) plus a thin LLM layer for ranking/formatting; build the arithmetic core first, standalone.

- Clarification node — LLM-generated follow-up questions, gated by the intent classifier's ambiguity signal.

- Memory — start with the simplest viable mechanism (session-scoped state dict) before building the cross-session conversation_summary persistence.

- Guardrails — a dedicated, independently unit-tested node (Section 14) that runs after generation, checking the draft answer against retrieved evidence programmatically.

- Human approval — the interrupt/resume flow; build last among the "control" nodes since it depends on the transfer-calculation path being stable first.

- Final response generator — the actual answer-composition prompt; deliberately built last so it has every upstream signal (rules, calculation, comparison, guardrail result, confidence) available to reference, rather than being designed against a guess of what will exist.

## 13.2 Why Bottom-Up, Not Top-Down

A team that starts by writing the "orchestrator" prompt first (a common instinct — "get the agent talking, then wire in real tools") ends up debugging two unknowns simultaneously: is the LLM's tool-selection reasoning wrong, or is the tool itself wrong? Building deterministic tools first and validating them independently means that by the time you wire up the LLM-driven nodes, any bug you see is very likely to be in the LLM's reasoning or prompt — a much narrower, faster debugging loop.

# 14. LangGraph Workflow

The node design mirrors the architecture document's Section 14, with implementation-level detail on state, retries, and recovery added here.

## 14.1 Node-by-Node Implementation Notes

| Node | Inputs (from state) | Outputs (to state) | Transitions | Retries/Fallbacks |
| --- | --- | --- | --- | --- |
| Intent Classification | user_query, conversation_summary | intent, intent_confidence | → Clarification if intent_confidence < threshold, else → Retrieval | On LLM API failure: 2 retries with exponential backoff, then fail the request with a 503 (never silently default to a guessed intent) |
| Clarification | intent, pending_question | follow_up_question | → back to Intent Classification once user responds | Max 1 clarification round; after that, proceed with the broadest reasonable interpretation rather than looping indefinitely (loop-prevention) |
| Retrieval | user_query, cards_owned filter | retrieved_chunks | → Rule Validation | On vector store timeout: 2 retries, then surface a 503 — never fall back to answering from the LLM's parametric memory |
| Rule Validation | retrieved_chunks | evidence_sufficient (bool), evidence_reason | → Calculation if sufficient, else → Insufficient-Info response | No retries needed (deterministic threshold check); this node must be pure and fast |
| Calculation | validated rule + spend_amount | calculation_result | → Comparison | Tool-level exceptions (bad input) surface as a validation error, not a silent default value — a calculation node must never "guess" a missing input |
| Comparison | multiple calculation_results | ranked_comparison | → Guardrail | N/A (pure function) |
| Guardrail | draft answer + retrieved_chunks + calculation_result | guardrail_passed (bool), violations[] | → Retrieval (loop, max 2 iterations) if failed, else → Approval or Final Answer | Loop prevention is critical here: cap at 2 guardrail-triggered retrieval loops, then hard-refuse rather than looping indefinitely |
| Human Approval | transfer_proposal | approval_status | → End (rejected) or Final Answer (approved) | Session timeout → discard state, do not auto-approve; this is a hard safety invariant, not a UX nicety |
| Final Answer | all upstream state | final_answer | → End | N/A |

## 14.2 State Design

Use a single typed state object (a TypedDict or Pydantic model) threaded through the entire graph — never pass ad-hoc dictionaries between nodes. This gives you static type-checking on every node's inputs/outputs (via mypy, Section 4) and makes the state schema a living, reviewable artifact (agents/state.py) rather than an implicit contract scattered across node implementations.

## 14.3 Loop Prevention as an Explicit Design Element

Two loops exist in the graph (Clarification→Intent, Guardrail→Retrieval). Both must have a hard iteration cap enforced in state (e.g., state.guardrail_loop_count), not just an assumption that the LLM "won't loop forever." Untested loop-prevention logic is one of the most common causes of a demo hanging or timing out in front of an audience.

# 15. Prompt Engineering Workflow

## 15.1 Prompt Inventory

| Prompt | Purpose | Key constraint to encode |
| --- | --- | --- |
| System prompt | Global behavior contract for the agent | "Answer only from retrieved evidence; never invent rates, partners, or exclusions; always show assumptions and confidence" |
| Intent classification prompt | Map query → one of a fixed enum of intents | Constrained output (structured output / function-calling schema), not free text, to avoid parsing ambiguity |
| Clarification prompt | Generate one focused follow-up question | Explicitly instructed to ask exactly one question, not a list |
| Retriever query-formation prompt (optional) | Rewrite a conversational query into a retrieval-optimized query | Only needed if evaluation shows raw user queries retrieve poorly (see Query Rewriting, Section 23) |
| Calculation-explanation prompt | Turn a calculator tool's structured output into a human-readable calculation walkthrough | Must not introduce any number not present in the tool's output — this prompt explains, it never computes |
| Comparison prompt | Rank and summarize multiple cards' calculated values | Must cite each card's source chunk, not just its number |
| Guardrail-check prompt (if any LLM-assisted checks are used alongside deterministic checks) | Judge whether a draft answer's claims are supported by retrieved evidence | Used only as a supplement to deterministic checks, never as the sole guardrail mechanism |
| Final answer composition prompt | Produce the user-facing response in the format specified in the architecture document (Section 13/14) | Fixed structure (recommended card, value, calculation, rules used, caps/exclusions, assumptions, alternatives, confidence) enforced via prompt + output validation |
| Evaluation prompt (for RAGAS-style automated grading) | Score faithfulness/relevancy of a generated answer against retrieved context | Kept entirely separate from the production prompts — evaluation prompts live in evaluation/, not agents/prompts/ |

## 15.2 Prompt Versioning

Store each prompt as a standalone, version-controlled file (agents/prompts/final_answer_v3.py, or a prompt-management table if the team wants runtime swapping without redeploying). Every prompt change that could affect output should be tagged in commit history and, ideally, re-run against the golden set before merging — treat prompt edits with the same rigor as code changes, because a "small wording tweak" is exactly the kind of change most likely to silently regress guardrail compliance.

# 16. API Development Workflow

Build the endpoints from the architecture document's Section 13 in this order: /health → /recommend → /cards → /user/profile → /optimize/monthly → /transfer/evaluate + /transfer/confirm → /feedback → /history → /admin/documents. This order front-loads the highest-value, highest-risk endpoint (/recommend) immediately after the trivial health check, and pushes admin/reporting endpoints (lower risk, well-understood CRUD patterns) to the end.

| Concern | Approach |
| --- | --- |
| Validation | Pydantic request/response models on every endpoint — reject malformed input at the edge, never inside business logic |
| Authentication | JWT bearer tokens from Stage 2 onward (per architecture doc FR-1); MVP can run single-user/no-auth locally |
| Pagination | Cursor-based pagination on /history (offset pagination degrades on large tables and is more prone to skipped/duplicated rows under concurrent writes) |
| Rate limiting | Per-user token bucket (e.g., slowapi for FastAPI) — primarily to bound LLM cost exposure, secondarily to prevent abuse |
| Error handling | Consistent error envelope ({"error": {"code": ..., "message": ...}}) across all endpoints, implemented once as FastAPI exception handlers, not repeated per-route |
| Versioning | URI-based (/api/v1/...) from day one, even with only one version — retrofitting versioning after a breaking change ships is far more painful than starting with it |
| Documentation | FastAPI's built-in OpenAPI/Swagger UI, kept accurate by relying on Pydantic models as the single source of truth rather than hand-written API docs that drift |

# 17. Frontend Development Workflow

## 17.1 MVP Scope: Streamlit

For Phase 1–3, a Streamlit app is the right choice — it is explicitly the tool recommended in the architecture document, and building a custom SPA before the backend/agent logic is proven would be solving the wrong problem first. Streamlit pages/components needed:

- Chat interface: the core interaction — a message list plus input box, calling /recommend (and follow-up endpoints for multi-turn flows).

- Recommendation cards: a structured rendering of the response schema (recommended card, value, calculation breakdown, rules used, assumptions, confidence) — do not just dump the raw LLM text; render the structured JSON response into a clear card layout, since the explainability requirement (architecture doc, Section 8) is a product requirement, not just a backend one.

- Confirm/Cancel buttons: for the Human Approval flow — these must block further interaction until resolved, matching the interrupt/resume semantics of the backend graph.

- Basic analytics view: a simple table/chart of past recommendations (/history), useful for both the user and for demoing FR-16.

- Admin panel: a minimal, separate Streamlit page (or a second app) for document upload and structured-rule review (Section 11.2) — kept intentionally simple; this is an internal tool, not a customer-facing surface.

## 17.2 State Management

Streamlit's built-in st.session_state is sufficient for the MVP's conversational state — do not reach for a heavier state-management library at this stage; it would be solving a problem Streamlit's model doesn't actually have yet.

## 17.3 Forms and Validation

Mirror backend Pydantic validation in the UI (e.g., reject negative spend amounts client-side too) for responsiveness, but always treat backend validation as the source of truth — never rely on client-side validation alone for anything that reaches the database or the LLM.

## 17.4 Future Evolution (Explicitly Out of Scope for MVP–Phase 3)

A Next.js (or similar) frontend is a reasonable Phase 4+/production evolution once the API contract (Section 16) has stabilized — building it earlier risks the frontend and backend contracts co-evolving painfully while the core agent logic is still changing weekly.

# 18. Testing Workflow

## 18.1 Test Pyramid for This Project

The pyramid is intentionally bottom-heavy: the calculator and chunking logic should have the largest number of fast, isolated unit tests, since they are the deterministic core the entire system's trustworthiness depends on.

## 18.2 Golden Dataset Creation (Do This Early, Not Last)

Start the golden dataset in Phase 1, not Phase 4 — write the 20 initial (query, expected retrieved rule, expected calculation, expected recommendation) tuples before the retriever is even fully built, based on manually reading the source PDFs. This ordering matters: a golden set written after the system exists tends to unconsciously encode the system's existing behavior (including its bugs) as "correct," rather than encoding ground truth independently derived from the source documents.

## 18.3 Test Types and Tooling

| Test type | Tooling | What it catches |
| --- | --- | --- |
| Unit | pytest | Calculator boundary conditions, chunking edge cases, individual node logic in isolation |
| Integration | pytest + a test Postgres instance (via testcontainers or a docker-compose test profile) | Retrieval→calculation→guardrail pipeline wiring bugs |
| Agent | pytest driving the compiled LangGraph graph directly (not through the API) | Branching logic (clarification, approval) exercised end-to-end without network/UI overhead |
| RAG evaluation | RAGAS or a custom harness against the golden set | Precision@K, recall@K, faithfulness, hallucination rate |
| Calculator evaluation | Direct comparison against hand-verified expected values | 100%-or-fail bar — no tolerance for arithmetic drift |
| Security | Manual red-teaming + a small suite of prompt-injection test cases embedded in test PDFs | Whether ingested document content can override system behavior |
| Load | Locust or k6 against the API | Behavior under concurrent users (connection pool exhaustion, latency degradation) |
| Regression | The full golden-set evaluation, re-run in CI on every PR that touches agents/, tools/, or rag/ | Silent regressions from prompt or retrieval changes |

## 18.4 CI Gating

Configure CI to block merges if calculation accuracy drops below 100% or hallucination rate rises above 0% on the golden set — these two metrics are non-negotiable given the domain, unlike, say, retrieval precision, which can reasonably have a softer, monitored-but-not-blocking threshold during early iteration.

# 19. Monitoring Workflow

| Concern | Approach |
| --- | --- |
| Logging | Structured (JSON) logs for every request: query, intent, retrieved chunk IDs, tool calls, final answer, latency, token usage — written to recommendation_logs (for product/audit use) and to a standard log stream (for operational debugging) |
| Tracing | LangSmith or Phoenix (open-source alternative) wired in from Phase 1 onward — do not defer tracing to Phase 3; debugging agent behavior without traces from the start makes early development significantly slower |
| Metrics | Track per-node latency, not just end-to-end latency — this is what lets you identify whether a slowdown is in retrieval, the LLM call, or the calculator |
| Token usage / cost tracking | Log tokens per call, tagged by node, so cost attribution is possible (e.g., "the final-answer generation step is 60% of our per-query cost") |
| Failure detection | Alert on: guardrail loop-cap hit rate rising, "insufficient information" rate rising sharply (may indicate a retrieval regression), LLM API error rate |
| User feedback | The /feedback endpoint (FR-9) writes directly into recommendation_logs, joined against the original query/answer, so feedback is always traceable to full context, not just a standalone rating number |

# 20. Deployment Workflow

## 20.1 Dockerization

A multi-stage Dockerfile (build stage installs dependencies, runtime stage copies only what's needed) keeps the deployed image lean. docker-compose.yml remains the primary local-dev and capstone-demo deployment mechanism; a more elaborate orchestration platform (Kubernetes) is explicitly out of scope at this project's scale — introducing it here would be solving a scaling problem the project doesn't have yet.

## 20.2 CI/CD Pipeline

GitHub Actions is the recommended CI/CD platform given its zero-setup integration with a GitHub-hosted repo and generous free tier for a capstone project's usage volume. Keep the pipeline linear and fast (target under 5 minutes for the lint+test stages) so it doesn't become a bottleneck the team learns to ignore.

## 20.3 Cloud Deployment

A single small VM or a managed container service (e.g., a basic App Runner/Cloud Run-style service) is sufficient. Database: a managed Postgres instance with pgvector support if available on the chosen provider, otherwise self-hosted Postgres on the same VM for capstone scale — do not over-provision for a load the project will never see during evaluation/demo.

## 20.4 Secrets in Deployment

Injected via the platform's secret manager as environment variables at container start — never baked into the Docker image, never committed, matching the local .env pattern from Section 4.

## 20.5 Rollback Strategy

Tag every deployed image with the Git commit SHA; keep the previous image available so a rollback is "redeploy the previous tag," not "revert code and rebuild under pressure." This is a five-minute setup cost that pays for itself the first time a bad deploy needs reverting during a demo week.

# 21. Development Timeline

A realistic 14–16 week schedule for a 1–2 person team at capstone pace, aligned to the phases in Section 3:

| Week | Focus | Milestone |
| --- | --- | --- |
| 1 | Phase 0: repo, Docker, CI skeleton, DB schema drafted | docker-compose up works; empty CI pipeline green |
| 2 | Data collection (Section 7) + PDF extraction pipeline (Section 8) | 4–5 cards' PDFs cleaned, chunked, metadata attached |
| 3 | Embeddings + pgvector storage (Sections 9–10) | Chunks embedded and queryable via raw similarity search |
| 4 | Calculator tool + unit tests; basic retriever function | Calculator has 100% test coverage on golden arithmetic cases |
| 5 | Wire retriever + calculator into a simple non-agent pipeline; start golden dataset | First 10 golden questions answerable end-to-end (no UI yet) |
| 6 | Finish 20 golden questions; Phase 1 acceptance criteria met | Milestone: Phase 1 (MVP) complete |
| 7 | LangGraph skeleton: Intent, Retrieval, Rule Validation, Calculation nodes | Agent graph replaces the linear pipeline for single-transaction queries |
| 8 | Comparison node; spend-category classifier; user_profiles table | Monthly-optimization use case answerable |
| 9 | Conversation memory; multi-turn clarification | Multi-turn scenarios from the architecture doc's Section 10 work correctly |
| 10 | Expand golden set to 40+; fix retrieval/chunking issues found | Milestone: Phase 2 complete |
| 11 | Guardrail node + unit tests independent of LLM output | Guardrail blocks a deliberately-injected bad-answer test case |
| 12 | Human Approval node (interrupt/resume) + transfer-strategy use case | Transfer queries correctly gate on explicit user confirmation |
| 13 | Streamlit UI wrapping the full API; LangSmith/Phoenix tracing wired in | Full demo flow runnable end-to-end via UI |
| 14 | Milestone: Phase 3 complete; begin full evaluation harness run | Hallucination rate and calculation accuracy measured against full golden set |
| 15 | Fix regressions found in evaluation; write README and architecture docs | Evaluation report finalized |
| 16 | Record demo video; final polish and buffer | Milestone: submission-ready |

# 22. Coding Standards

## 22.1 Architecture Principles

- Separation of concerns (Section 1.2) is the single most important principle for this project specifically — enforce it in code review as strictly as any style rule.

- Dependency direction: agents/ may depend on tools/ and database/; tools/ must never depend on agents/ — this one-way dependency is what keeps tools independently testable and reusable.

## 22.2 SOLID, DRY, KISS — Applied Pragmatically

- Single Responsibility: each LangGraph node does exactly one thing (the node table in Section 14 is effectively a Single-Responsibility checklist).

- Open/Closed: the calculator should be extensible to new reward_unit types (miles, cashback, points) without modifying its core arithmetic loop — use a small strategy/lookup pattern for unit conversion rather than a growing if/elif chain.

- DRY, with restraint: apply the "rule of three" (Section 2.2) — don't abstract shared logic until a third caller needs it; premature abstraction in a fast-moving capstone project costs more than the duplication it prevents.

- KISS: resist Section 23's suggestions until the MVP is stable — every one of them is individually reasonable and collectively a scope-creep risk.

## 22.3 Clean Architecture Framing

This project's dependency structure (API → Services → Tools/Repositories → Database) is a lightweight, pragmatic application of Clean Architecture's dependency-inversion idea, without adopting its full ceremony (no strict "entities/use-cases/interface-adapters" folder taxonomy) — right-sized for the team and timeline.

## 22.4 Error Handling and Logging Standards

- Never swallow an exception silently (except: pass is banned in code review).

- Every caught exception at a service boundary is logged with enough context (query ID, user ID if available, node name) to reproduce the failure from logs alone.

- Log levels used consistently: DEBUG for chunk-level retrieval detail, INFO for request lifecycle events, WARNING for guardrail triggers/refusals, ERROR for system failures.

## 22.5 Documentation Standards

Every tool function (calculator.py, retriever.py) has a docstring specifying inputs, outputs, and failure modes — since these are the functions most likely to be reused or referenced outside their original context (evaluation scripts, future interfaces).

# 23. Suggestions & Best Practices

| Suggestion | Why useful | Complexity | Priority | When |
| --- | --- | --- | --- | --- |
| Hybrid search (BM25 + vector) | Catches exact-term queries (merchant names, card names) embeddings under-rank | Medium | Should Have | Phase 2 |
| Query rewriting | Improves retrieval for conversational, underspecified queries | Medium | Should Have | Phase 2 |
| Context compression | Reduces token cost and noise when many chunks are retrieved | Medium | Nice to Have | Phase 2/3 |
| Rerankers (Cohere, BGE reranker) | Improves precision of final top-K after initial retrieval | Medium | Should Have | Phase 2 |
| Knowledge graph integration | Could model transfer-partner relationships more richly than flat tables | High | Nice to Have | Production (only if scaling to many issuers/partners) |
| MCP (Model Context Protocol) support | Standardizes tool exposure if integrating with external agent ecosystems later | Medium | Nice to Have | Production |
| Real-time reward updates | Removes staleness risk entirely | High (requires issuer API access, largely unavailable) | Nice to Have | Future Scope (architecture doc, Section 23) |
| OCR fallback for scanned PDFs | Prevents silent data loss from non-text-layer documents | Low-Medium | Should Have | MVP (as a guard, per Section 8.6), full pipeline Phase 2 |
| Cost optimization (model tiering: cheap model for classification, strong model for final answer) | Meaningfully reduces per-query LLM spend | Low | Must Have | MVP |
| Response caching | Avoids recomputation for identical repeated queries | Low | Should Have | Phase 2 |
| Background jobs (Celery/RQ) | Needed once ingestion or evaluation runs become long-running/async | Medium | Should Have | Phase 2 (for ingestion), Production (for scheduled re-evaluation) |
| Redis caching | Backing store for response caching and rate limiting | Low | Should Have | Phase 2 |
| Feature flags | De-risks rolling out guardrail/prompt changes without a full deploy | Low | Should Have | Phase 2/3 |
| A/B testing | Useful once there's real user traffic to compare prompt/model variants against | High (needs traffic + stats rigor) | Nice to Have | Production |
| User analytics | Informs which categories/cards need better data coverage | Low-Medium | Should Have | Phase 3 |
| Feedback learning loop | Turns /feedback data into actual golden-set/prompt improvements | Medium | Should Have | Phase 3/Production |
| Multi-LLM support | Reduces vendor lock-in risk (architecture doc risk analysis) | Medium | Nice to Have | Production |
| Explainability dashboard | Makes the "why" behind recommendations inspectable at a glance, reinforcing the project's core trust thesis | Medium | Should Have | Phase 3 |
| Agent memory improvements (vector-based long-term memory vs. flat summary) | More scalable personalization as conversation history grows | High | Nice to Have | Production |
| Observability with LangSmith/Phoenix | Already covered as Must Have from Phase 1 (Section 19) — listed here for completeness | Low | Must Have | MVP |
| Security hardening (input sanitization, prompt-injection defenses, secrets audit) | Directly mitigates the P0 risks in the architecture document's risk analysis | Medium | Must Have | Phase 3 |
| Financial compliance considerations (disclaimers, scope-limitation language, audit trail) | Directly mitigates the compliance risk flagged throughout the architecture document | Low | Must Have | MVP (disclaimers), Phase 3 (full audit trail via recommendation_logs) |

How to use this table: at the start of each phase in Section 3, filter this table to that phase's "When" column and treat only those rows as in-scope. Everything else is explicitly deferred, not forgotten — this table itself is the record.

# 24. Common Pitfalls

| Pitfall | Why it happens | How to avoid it |
| --- | --- | --- |
| Letting the LLM do arithmetic "just this once" | Feels faster than routing through the calculator tool for a simple case | Enforce via code review and a guardrail check that flags any numeric claim not traceable to a tool output |
| Treating the golden dataset as a Phase 4 afterthought | Testing feels less urgent than "making it work" | Start the golden set in Phase 1 (Section 18.2) — it is a specification, not just a test suite |
| Building the full LangGraph graph before validating retrieval quality | Agent orchestration is the "exciting" part to build | Follow the bottom-up order in Section 13.1; prove retrieval and calculation work as plain functions first |
| Weakening guardrails under demo-day time pressure | A guardrail blocking an answer looks like a bug when you're rushing | Treat every guardrail trigger as a signal to fix the underlying data/retrieval issue, never as a rule to loosen |
| Naive fixed-length chunking without inspecting the results | Chunking "ran without errors," so it's assumed to be fine | Manually spot-check chunks against source PDFs (Section 8.7) — a silent chunking failure is invisible until a specific evaluation question exposes it |
| Skipping metadata filtering on retrieval | Vector similarity alone often "looks" like it's working with only 1–2 cards loaded | Add card_name filtering from day one, even with a small corpus — the bug is latent, not absent, at small scale |
| No loop-prevention caps on graph cycles | Assuming the LLM "won't" loop forever | Add explicit iteration counters in state (Section 14.3) before the first demo, not after the first hang |
| Scope-creeping from the Suggestions list (Section 23) mid-phase | Every suggestion is individually a good idea | Gate additions strictly by the "When" column; treat mid-phase additions as a phase-planning failure to correct, not a one-off exception |
| Committing secrets or real card PDFs with unclear redistribution rights to a public repo | Convenience during fast iteration | .gitignore discipline from Phase 0; store raw PDFs outside the repo (Section 7.4) |
| Deploying without a tested rollback path | Rollback feels like a "later" concern | Set up commit-SHA-tagged image rollback (Section 20.5) in the same PR that sets up initial deployment, not afterward |

# 25. Final Technical Recommendations

## 25.1 Ratings

| Dimension | Rating (/10) | Rationale |
| --- | --- | --- |
| Overall architecture | 8 | Clean separation of facts/arithmetic/judgment; vertical-slice delivery reduces integration risk |
| Scalability | 6 | Appropriate for capstone scale; several explicitly-flagged migration points (pgvector → dedicated vector DB, manual → AI-assisted extraction) exist for growth |
| Maintainability | 8 | Strong module boundaries (tools/ vs agents/), typed state, and a documented dependency direction |
| AI engineering maturity | 8 | Demonstrates the full modern stack (RAG, agents, tool use, guardrails, human-in-the-loop, evaluation) applied with real engineering discipline rather than superficially |
| Production readiness | 5 | Solid foundation, but genuinely production-grade status requires the Phase-3-and-beyond items in Section 23 (security hardening, compliance review, real monitoring/alerting) |
| Security readiness | 6 | Core patterns are right (secrets management, prompt-injection awareness); needs a dedicated hardening pass (Section 23) before any real deployment beyond a demo |
| Resume impact | 8 | The "irreversibility-gated human approval" and "separation of facts/arithmetic/judgment" narratives are genuinely differentiated talking points |
| Portfolio impact | 8 | End-to-end, demoable, and defensible in an interview at both the product and engineering-decision level |

## 25.2 Prioritized Implementation Checklist (Development Tracker)

Must complete before calling it an MVP:

- [ ] Repo, Docker, CI skeleton (Phase 0)

- [ ] 4–5 cards ingested with validated, spot-checked chunks

- [ ] Calculator tool with 100% unit test pass rate

- [ ] Retriever with metadata (card_name) filtering

- [ ] 20-question golden dataset, hand-derived from source PDFs

- [ ] /recommend endpoint answering all 20 golden questions correctly and with citations

Must complete before calling it "agentic" (Phase 2):

- [ ] LangGraph graph with Intent, Retrieval, Rule Validation, Calculation, Comparison nodes

- [ ] Conversation memory (session-scoped, minimum)

- [ ] Monthly-optimization use case working end-to-end

- [ ] Golden set expanded to 40+ questions

Must complete before calling it "safe" (Phase 3):

- [ ] Guardrail node, independently unit-tested

- [ ] Human Approval interrupt/resume flow for transfer strategies

- [ ] Streamlit UI with confirm/cancel gating

- [ ] LangSmith/Phoenix tracing live

- [ ] Loop-prevention caps verified under test

Must complete before calling it "submittable":

- [ ] Full evaluation harness run: 0% hallucination rate, 100% calculation accuracy on golden set

- [ ] README allowing a clean-clone run in under 30 minutes

- [ ] Architecture diagrams and demo video

- [ ] Rollback-capable deployment demonstrated at least once

Explicitly deferred (do not start early): everything in Section 23 marked "Nice to Have" or "Production," and anything in the architecture document's Future Scope (Section 23 of that document).

End of document. This guide is designed to be read alongside the companion Solution Architecture & Product Documentation — this document answers "how do we build it, in what order, and why," while the companion answers "what are we building and what does it need to do."